## Slide 1
Supplier-Status Dashboard Pilot Launch
A focused four-week pilot to eliminate fragmented information and reclaim staff time.

## Slide 2
The Problem: Fragmented Information
74
Status-Check Messages
Sent in the last reporting cycle alone
~50%
Duplicate Requests
Asked for information another team already had
9
Staff-Hours Per Week
Lost to repeated status checks

## Slide 3
Why It Happens
Information is scattered across teams with no shared view of the full picture. No single team sees the complete picture — so everyone keeps asking.
Team A
Knows the request status
Team B
Knows the deadline
Team C
Owns the next action

## Slide 4
The Solution: One Weekly Dashboard
One internal view answers the question every team is already asking: "What needs attention before the next deadline?" No more cross-team message chains — the answer is already there.
Request Status
Open • Waiting • Complete
Deadline & Owner
Due date with assigned owner
Next Action Needed
Clear next task to resolve

## Slide 5
Three Concrete Benefits
Account Managers
Earlier visibility. Check one view instead of asking multiple people across email threads.
Account-Service Staff
Fewer repeated messages. No need to re-answer the same questions across separate threads.
Reporting Operations
Clearer ownership. Easier handoffs and fewer last-minute scrambles before deadlines.

## Slide 6
What the Dashboard Is Not
Not a replacement for official reports or account-service processes
Not shared with clients during the pilot
Not a record of shipment instructions, orders, or account details
All data sanitized and approved per internal rules

## Slide 7
Four-Week Pilot Schedule
Week 0
Confirm pilot users & send user guide.
Week 1
Dashboard goes live; log issues.
Week 2
Review field labels & fix confusion.
Week 3
Verify owner & deadline fields.
Week 4
Review results — continue, revise, or stop.

## Slide 8
Success Metric & Support
30% Target Reduction
In repeated status-check messages over the four-week pilot period. This is the primary measure of success.
Weekly Updates
Reporting operations refreshes all status fields once per week — a predictable, low-overhead cadence.
Dedicated Feedback Channel
Each pilot team has one named account manager contact plus a short feedback form for quick issue reporting.

## Slide 9
Three Pilot Checks
At the end of Week 4, the review will answer three questions. These are the criteria that determine whether the pilot succeeds.
1
Message Volume
Are repeated status-check messages measurably reduced?
2
Field Clarity
Do users understand the fields without additional explanation?
3
Operational Load
Does the weekly update process create too much work for reporting operations?

## Slide 10
Next Steps
Three decisions needed from this room to move forward.
Today
Confirm pilot teams: Team North and Team West
By Friday
User list, access plan, and feedback form ready
Monday
Pilot launches. Dashboard goes live.
Your confirmation today keeps the Monday launch on track. No further approvals needed after this meeting.