## Slide 1: Approve a Four-Week Workflow Pilot
Reducing import document handoff delays Decision today: pilot, owner, review measures

## Slide 2: Handoff Notes Are Spread Across Three Places
Email: messages split Spreadsheet: copied details Short messages: owner unclear Emphasis: ownership is unclear before the cutoff window

## Slide 3: Most Delays Involve Unclear Handoff Notes
38 late handoffs 61% linked to unclear notes 22 minutes average rework Emphasis: unclear notes are the main preventable cause

## Slide 4: One Shared Log Makes Ownership Visible Earlier
Current
Email check Manual note Handoff Deadline risk
Pilot
Exception log Fixed checkpoint Visible owner Control unchanged

## Slide 5: The Pilot Is Limited and Controlled
Week 0: review fields Weeks 1-4: daily checkpoint End: review delay, rework, and feedback Emphasis: test before expanding

## Slide 6: The Request Is Approval, Ownership, and Review Criteria
Approve the pilot Confirm the documentation lead Agree the review measures